SAPZ PROGRAMME — REF: NPCO/SAPZ/IFAD/26/1023/588

Enterprise Architecture & Digital Transformation Blueprint

Enterprise System Management (ESM) Platform and Central Knowledge Repository (CKR)

Section 13 of 16 — Implementation Blueprint

Prepared for the SAPZ National Programme Coordination Office — Consultant: Ahmed Babajide Olanrewaju

# 13.1 Implementation Approach

This section takes the five-phase Phase 1 delivery timeline fixed in Section 11.4 and the governance model fixed in Section 12 and specifies exactly how they are executed: in what order architecture layers are built, what work packages populate each phase, which specific work sits on the critical path, what resources are required, and the quality gates that must pass before the next phase begins. It answers the question Section 11 leaves at the roadmap level — what happens, by when — at the level of detail a delivery team would need to actually start work in Week 1.

# 13.2 Architecture Layers and Build Sequence

Six architecture layers are built in a fixed sequence, each depending on the layer before it, consistent with the layer-by-layer thinking sequence fixed at the outset of this Blueprint (Section 1).

| # | Layer | What Is Built | Depends On |
| --- | --- | --- | --- |
| 1 | Governance and Information Foundation | Data & Content Governance Charter signed; shared taxonomy and metadata standard drafted (Sections 2.10, 5.5). | Nothing — this is the foundation layer. |
| 2 | Identity and Security Baseline | Keycloak deployed; RBAC/ABAC roles defined; MFA enrolled for privileged roles (Sections 8.3, 10.9). | Layer 1 (roles reference taxonomy-scoped state affiliations). |
| 3 | Core Application Platforms | ESM Core Platform (Node.js) and CKR Core Platform (Laravel) configured per Section 10's recommended stack. | Layer 2 (applications require identity integration from first deployment). |
| 4 | Data Migration and Content Population | Legacy content audited, classified, migrated, and validated per the five-stage process in Section 6.8. | Layer 3 (a target platform must exist before content is migrated into it). |
| 5 | Integration and Functional Modules | The Integration & API Gateway and the twenty-eight functional modules (Section 4) configured on top of the populated core platforms. | Layer 4 (functional modules operate on classified, migrated content). |
| 6 | Testing, Training, and Handover | Continuous and formal testing, training-of-trainers delivery, user acceptance, and the documented handover package (Section 11.12). | Layer 5 (a fully configured, populated system is required before it can be meaningfully tested or trained on). |

This build sequence is why the Governance Charter is signed in Week 2, not deferred: every later layer depends on the taxonomy and decision-rights structure Layer 1 establishes, so any delay to Layer 1 propagates through all five subsequent layers — the specific mechanism behind the Critical Path analysis in Section 13.5.

# 13.3 Work Package Breakdown

Thirteen work packages populate the five Phase 1 delivery phases fixed in Section 11.4, each mapped to the architecture layer it builds (Section 13.2).

| ID | Work Package | Phase | Layer | Key Dependency |
| --- | --- | --- | --- | --- |
| WP1 | Stakeholder consultation (seven states + FCT) | 1 (Wks 1–2) | — | None — first activity |
| WP2 | Content and data audit | 1 (Wks 1–2) | — | WP1 (consultation informs audit scope) |
| WP3 | Governance Charter drafting and adoption | 1 (Wks 1–2) | Layer 1 | WP1, WP2 |
| WP4 | Shared taxonomy and metadata standard finalization | 1 (Wks 1–2) | Layer 1 | WP3 |
| WP5 | Identity platform deployment and role design | 2 (Wks 3–8) | Layer 2 | WP4 |
| WP6 | ESM and CKR core platform configuration | 2 (Wks 3–8) | Layer 3 | WP5 |
| WP7 | Content migration (Must Have priority subset) | 2 (Wks 3–8) | Layer 4 | WP6 |
| WP8 | Workflow and integration configuration | 2 (Wks 3–8) | Layer 5 | WP7 |
| WP9 | Functional module configuration (twenty-eight modules) | 2 (Wks 3–8) | Layer 5 | WP8 |
| WP10 | Continuous testing (beginning Week 3) | 2–3 (Wks 3–10) | Layer 6 | Runs alongside WP6–WP9, per Section 11.4's risk-reduction note |
| WP11 | Formal test cycle and defect resolution | 3 (Wks 9–10) | Layer 6 | WP9, WP10 |
| WP12 | Training-of-trainers delivery and user acceptance testing | 4 (Wk 11) | Layer 6 | WP11 |
| WP13 | Go-live, final reporting, and documented handover | 5 (Wk 12) | Layer 6 | WP12 |

# 13.4 Milestones

Five milestones gate phase transitions, identical to those fixed in Section 11.4, restated here against their governing work packages.

| Milestone | Week | Confirmed By |
| --- | --- | --- |
| Governance Charter signed | 2 | WP3 complete; co-signed by KMC, endorsed by National Programme Coordinator |
| Core platforms configured; priority content migrated | 8 | WP6 and WP7 complete and validated |
| Test cycle complete | 10 | WP11 complete; defects triaged and resolved |
| User acceptance confirmed | 11 | WP12 complete; KM and ICT Units certified on core administration tasks |
| Go-live and handover accepted | 12 | WP13 complete; handover package formally signed off (Section 11.12) |

# 13.5 Critical Path

Six work packages sit on the critical path — the sequence whose total duration determines whether the twelve-week schedule holds. A delay to any one of these six delays go-live directly; every other work package carries some schedule float.

| Critical Path Work Package | Why It Is Critical |
| --- | --- |
| WP3 — Governance Charter adoption | Every later layer depends on the taxonomy and decision-rights structure this establishes (Section 13.2, Layer 1); no configuration work can meaningfully begin without it. |
| WP5 — Identity platform deployment | Every application in the portfolio requires identity integration from first deployment (Section 3.3); this cannot be retrofitted efficiently after platforms are configured. |
| WP6 — Core platform configuration | The single largest work package by effort, and the direct prerequisite for content migration, workflow configuration, and every functional module. |
| WP7 — Content migration (priority subset) | The Master Bid & Delivery Strategy's own scenario planning identifies legacy content quality as the highest-risk variable in the entire engagement; delay here has historically been the most common source of schedule slippage in comparable programmes (Section 10 benchmarking). |
| WP11 — Formal test cycle | Cannot be compressed without accepting materially higher go-live risk; this is why continuous testing (WP10) begins in Week 3 rather than only within the formal window, to reduce — though not eliminate — this work package's own schedule risk. |
| WP13 — Go-live and handover | The terminal milestone; by definition, any upstream delay arrives here. |

The single highest-leverage schedule protection in this plan is starting WP1 (stakeholder consultation) immediately and without delay in Week 1: every critical path work package traces back to it, and the Master Bid & Delivery Strategy's own base-case scenario planning specifically flags stakeholder consultation across seven states as likely to take longer than the two weeks nominally allotted.

# 13.6 Resource Requirements

Resource requirements follow the RACI structure fixed in Section 2.13, stated here in terms of effort and role rather than accountability alone.

| Resource | Role | Commitment |
| --- | --- | --- |
| Consultant (named individual) | Leads architecture, configuration, and migration personally throughout | Full-time, twelve weeks, per the resource-loading discipline fixed in the Master Bid & Delivery Strategy |
| Bounded specialist support (if engaged) | Named, defined-scope support for specific modules only, where resource-loading requires it | Part-time, scoped to specific work packages — not a standing team, consistent with the CV-only, individual-consultant nature of this engagement |
| KM and ICT Units | Consulted and increasingly Responsible across WP5–WP13, per the capability-maturity progression (Section 11.10) | Part-time during Phase 1, rising to full ownership at handover |
| State-level focal points (seven states + FCT) | Consulted on migration and classification decisions; participate in training and UAT | Time-bounded participation at defined points, not continuous |
| National Programme Coordinator / KMC | Governance decisions and milestone sign-off per the Decision Model (Section 2.9) | Periodic, at each governance touchpoint and milestone |
| Cloud infrastructure | Azure environment (Section 10.7) provisioned for development, staging, and production | Provisioned by Week 3, ahead of WP6 |

# 13.7 Execution Risks and Mitigation (Summary)

Three risks concentrate specifically at the implementation level, distinct from the full architecture risk register developed in Section 14. Each is already anticipated in the critical path analysis above.

| Risk | Mitigation |
| --- | --- |
| Legacy content messier than expected (WP7) | Prioritized-subset migration scope (Section 3.2 MoSCoW) absorbs quality variance without threatening the Must Have commitment; full coverage is explicitly a post-handover medium-term improvement (Section 11.6). |
| Stakeholder consultation across seven states takes longer than two weeks (WP1) | WP1 begins immediately in Week 1 with no lead-in delay; the critical path analysis (Section 13.5) already treats this as the highest-leverage schedule protection point. |
| Key-person risk (a single named consultant delivering the entire engagement) | Bounded, named specialist support for specific work packages only (Section 13.6), sequenced work rather than parallel dependency on the consultant alone, and comprehensive documentation (Section 11.12) reducing reliance on undocumented individual knowledge. |

Section 14 (Architecture Risks) develops the complete risk register — architectural, operational, and strategic — of which these three implementation-specific risks are a subset.

# 13.8 Technical Debt Strategy

Technical debt in this engagement is managed as a deliberate, documented category, not an unplanned byproduct discovered after the fact. Every MoSCoW Should Have item deferred beyond Week 12 — full migration coverage, the full analytics dashboard suite, comprehensive training-manual coverage for every role (Section 3.2) — is logged as intentional technical debt in the Decision Register (Section 4.4), with a named owner and a target resolution point drawn from the medium-term improvements roadmap (Section 11.6), rather than left as an implicit gap discovered later during a security or architecture review. No debt is carried silently: the Architecture Review Report in Section 15 audits this Decision Register log specifically as part of its own quality assurance pass, so that deferred scope remains visible rather than forgotten.

# 13.9 Quality Gates

Each phase transition in Section 11.4 is gated by explicit pass criteria; the next phase does not begin until its gate criteria are met.

| Gate | Pass Criteria |
| --- | --- |
| Phase 1 → Phase 2 | Governance Charter signed (WP3); shared taxonomy finalized (WP4). |
| Phase 2 → Phase 3 | Core platforms configured and validated (WP6); Must Have priority content migrated and reconciled per Section 6.8 Stage 4 (WP7); workflow and functional modules configured (WP8, WP9). |
| Phase 3 → Phase 4 | Formal test cycle complete with all Critical and High severity defects resolved (WP11); security testing against the Section 8 threat model passed. |
| Phase 4 → Phase 5 | User acceptance confirmed by state-level focal points (WP12); KM and ICT Units certified on core administration tasks. |
| Phase 5 → Closure | Go-live confirmed stable; handover package delivered and formally signed off (WP13, Section 11.12). |

# 13.10 Acceptance Criteria

Final programme acceptance requires four conditions to hold simultaneously, consistent with the Success Metrics fixed in Section 11.13: every Must Have application, module, and integration point identified in Sections 3.2 and 4.1 is live and functioning; the Governance Charter is signed and operating, with the KMC and KM and ICT Units actively exercising the Decision Rights fixed in Section 12.3; the handover package (Section 11.12) is delivered in full and formally accepted by the National Programme Coordinator; and no Critical or High severity defect or security finding remains open. Acceptance against a prioritized Should Have subset — full migration coverage, the complete analytics suite — is explicitly not required for programme acceptance, consistent with the Technical Debt Strategy above; those items are tracked to their own medium-term resolution point rather than blocking go-live.

# 13.11 Transition to Section 14

Section 14 (Architecture Risks) develops the complete risk register this section's Section 13.7 summary is drawn from — architectural, operational, and strategic risks across the full lifecycle of this Blueprint, each with likelihood, impact, and a named mitigation owner.