SAPZ PROGRAMME — REF: NPCO/SAPZ/IFAD/26/1023/588

Enterprise Architecture & Digital Transformation Blueprint

Enterprise System Management (ESM) Platform and Central Knowledge Repository (CKR)

Section 14 of 16 — Architecture Risks

Prepared for the SAPZ National Programme Coordination Office — Consultant: Ahmed Babajide Olanrewaju

# 14.1 Risk Management Approach

This section is the complete architecture risk register for this Blueprint — architectural, technical, data, security, integration, operational, governance, schedule, and Phase 2 risks across the full lifecycle of the ESM/CKR programme, not only the implementation-execution risks already summarized in Section 13.7. Every risk is scored on a simple three-level Likelihood × Impact scale (Low, Medium, High), consistent with the probability-impact matrix methodology already applied in the Master Bid & Delivery Strategy, and every risk carries a named mitigation and a named owner drawn from the Organisation Model (Section 2.7) — no risk in this register is left without an accountable party.

This register is the source document the Risk Register functional module (Section 4.4, module 21) is built to operate: every risk below is intended to be entered into that module at the start of the engagement and tracked through its own lifecycle (Identify → Assess → Mitigate → Monitor → Close, per Section 2.5), rather than existing only as a static document.

# 14.2 Strategic Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | Scope creep beyond the Phase 1 Must Have baseline (Section 3.2) as stakeholders request additional features during the build. | Medium | Medium | The MoSCoW prioritization (Section 3.2) and Phase Discipline principle (Section 1.7) are invoked explicitly at every scope discussion; new requests are logged as Phase 2 roadmap candidates (Section 11.7), not silently absorbed. | National Programme Coordinator and KMC (jointly, per Section 2.9) |
| R-02 | A donor fiduciary or compliance gap (NDPR, IFAD AML/Anti-Fraud/PSEA) surfaces late in the engagement or during a post-go-live supervision mission. | Low | High | The Standards and Policies Registry (Section 12.5) and NDPR compliance checklist (Section 4.4) are reviewed at each governance milestone (Section 12.8), not only at go-live. | KMC |

# 14.3 Architectural and Technical Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-03 | Maintaining two backend frameworks (Laravel and Node.js, Section 10.2) increases long-term maintenance complexity for KM and ICT Units beyond what a single-framework stack would require. | Medium | Medium | The trade-off was accepted deliberately (Section 10.14) because each framework fits its own system's TOR-mandated constraint; documentation and training (Section 11.11) explicitly cover both stacks rather than assuming one is primary. |
| R-04 | The managed container service (Section 10.6) proves insufficiently flexible if the programme's technical footprint grows faster than the Section 11 roadmap projects. | Low | Medium | The Technology Stack Evaluation (Section 10.6) already names full Kubernetes as the fallback option, to be revisited against actual evidence of scale rather than adopted speculatively now. |
| R-05 | OpenSearch (Section 10.4) develops a meaningful feature gap against ElasticSearch for a future need not anticipated at evaluation time. | Low | Low | The vendor lock-in mitigation principle (Section 3.1) was weighed against this risk explicitly at evaluation time and judged the better trade-off; OpenSearch's open-source trajectory is monitored as part of routine platform administration (Section 4.5). |

# 14.4 Data and Information Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-06 | Legacy content migration (Section 6.8) reveals data quality substantially worse than the Weeks 1–2 audit estimated, consistent with the Master Bid & Delivery Strategy's own scenario planning. | Medium-High | High | Prioritized-subset migration scope (Section 3.2 MoSCoW) absorbs quality variance without threatening the Must Have commitment; Migration Stage 4 validation (Section 6.8) catches quality issues before legacy retirement. |
| R-07 | The shared taxonomy (Section 5.5) is applied inconsistently across seven states and the FCT during early capture, before classification discipline matures. | Medium | Medium | Mandatory metadata fields block submission until populated (Section 6.6); steward and editorial review validate classification before publication or approval (Section 5.7); periodic sampling audits classification accuracy. |
| R-08 | Personal data is inadvertently published to the public CKR before the redaction check (Section 6.11) is consistently applied by all editorial reviewers. | Low | High | Editorial review explicitly includes the redaction check as a named workflow step (Section 5.7), not an optional judgment call; NDPR compliance training is part of the progressive Training module rollout (Section 4.6). |

# 14.5 Security Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-09 | Credential compromise via phishing targeting state-level users with lower digital-security exposure, per the threat model (Section 8.6). | Medium | High | Mandatory MFA for privileged roles (Section 8.3); progressive security-awareness training (Section 8.13) delivered alongside each build phase, not compressed into Week 12. |
| R-10 | An over-privileged account goes undetected between quarterly access reviews (Section 8.13), enabling an insider threat. | Low | High | Least Privilege principle applied at role design (Section 8.1); Audit module logs every access event (Section 8.8), enabling detection between formal review cycles. |
| R-11 | The public CKR experiences a denial-of-service event during a high-visibility programme milestone or donor supervision mission. | Low | Medium | Rate limiting at the Integration & API Gateway (Section 7.5); cloud-first managed infrastructure (Section 1.7) with elastic capacity absorbs volumetric spikes. |

# 14.6 Integration Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-12 | The SAPZ Public Website integration (Section 7.3, profile #1) breaks due to an undocumented, website-side change outside this engagement's control. | Medium | Medium | The interface contract (Section 7.6) is versioned and documented; the integration degrades gracefully (Section 3.4) rather than failing CKR's own operation if the website side is unavailable. |
| R-13 | Future ERP, MIS, or M&E system integration assumptions (Section 7.4, profile #11) prove incorrect once a specific system is actually identified. | Medium | Low | No integration design work is performed speculatively ahead of a named system; the placeholder is explicitly scoped as Could Have / Phase 2 (Section 3.2), avoiding wasted design effort against an unknown target. |

# 14.7 Operational and Sustainability Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-14 | KM and ICT Units do not reach Level 3 maturity within the 12-month target (Section 11.10), prolonging informal dependency on the consultant beyond the documented handover boundary. | Medium | Medium | Three-checkpoint capacity-building tracking (Section 11.10); training-of-trainers model transfers capability progressively rather than at a single Week 12 event; the Won't Have boundary (Section 3.2) is stated explicitly to both parties from the outset. |
| R-15 | Key-person risk: the named consultant becomes unavailable (illness, competing commitment) mid-engagement, with no subcontracted specialist covering the affected work. | Low | High | Bounded, named specialist support for specific work packages (Section 13.6); comprehensive architecture and configuration documentation (Section 11.12) reduces reliance on undocumented individual knowledge. |

# 14.8 Governance Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-16 | The Governance Charter (Section 2.10) is signed at Inception but not actively enforced once post-handover attention moves elsewhere, allowing fragmentation to quietly re-emerge. | Medium | High | Annual Governance Charter renewal review (Section 12.8) and the Enterprise Architecture Review Board's ongoing mandate (Section 12.6) give the Charter a recurring enforcement checkpoint, not a one-time signature. |
| R-17 | The Enterprise Architecture Review Board meets irregularly after handover, undermining the Architecture Review Process (Section 12.7) it exists to run. | Medium | Medium | Board review is tied to fixed calendar triggers (Section 12.8) — milestones during Phase 1, and the 12-month Phase 2 activation decision post-handover — rather than left to ad hoc scheduling. |

# 14.9 Schedule and Delivery Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-18 | Stakeholder consultation across seven states and the FCT (WP1, Section 13.3) overruns the two weeks nominally allotted, delaying every downstream critical-path work package (Section 13.5). | Medium | High | WP1 begins immediately in Week 1 with no lead-in delay — the single highest-leverage schedule protection identified in Section 13.5; consultation logistics are planned before contract signature where possible. |

# 14.10 AI and Phase 2 Risks

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-19 | A Phase 2 AI capability (Section 9) is deployed before the Phase 1 information architecture foundation it depends on (taxonomy consistency, classification quality) is actually mature enough to support it. | Low | Medium | Each AI capability's Phase 1 foundation is named explicitly in its own profile (Section 9.3); Knowledge Discovery and Predictive Analytics are specifically sequenced for introduction only after sufficient operating history and classification quality are confirmed (Sections 9.4, 9.6). |

# 14.11 Top Risks — Deep-Dive

Three risks carry the combination of likelihood and impact that warrants deeper treatment beyond the register entry above.

## R-06 — Legacy Content Migration Quality

| Situation | The Master Bid & Delivery Strategy's own base-case scenario planning explicitly expects the legacy document base across seven states and the FCT to be 'messier than ideal but not unmanageable' — this is not a hypothetical risk but an anticipated condition. |
| --- | --- |
| Potential Impact | Poor-quality legacy content, if migrated without adequate validation, would populate the new centralized repository with the same disorganization it was built to replace, undermining the programme's core value proposition. |
| Mitigation | The five-stage migration process (Section 6.8) exists specifically to manage this risk: Audit and Classify stages surface quality issues before migration itself; Validate (Stage 4) reconciles record counts and samples accuracy; the Must Have priority-subset scope (Section 3.2) ensures the highest-value content receives the most careful handling first. |
| Residual Risk | Accepted as Medium: full legacy coverage remains a medium-term improvement (Section 11.6) precisely because some quality issues will likely require more remediation time than the twelve-week schedule allows for the complete corpus. |

## R-16 — Governance Charter Enforcement Erosion

| Situation | A signed governance instrument that is not actively used loses its practical authority over time, particularly once the consultant's direct engagement ends and institutional attention naturally shifts to new priorities. |
| --- | --- |
| Potential Impact | This is the single risk that, if realized, would undo the central thesis of this entire Blueprint: that the programme's coordination failures are governance failures, and that a signed Charter is what prevents fragmentation from quietly reappearing in digital form. |
| Mitigation | The Charter is embedded in recurring, calendared governance activity (Section 12.8) — annual renewal review, quarterly donor-alignment touchpoints, milestone-triggered Board reviews — rather than treated as a one-time deliverable; the Enterprise Architecture Review Board's ongoing mandate gives it an active body to answer to, not just a document to reference. |
| Residual Risk | Accepted as Medium: no architecture document can fully guarantee an institution's own follow-through after a twelve-week engagement ends; this is a genuine limit of what any consultant-delivered Blueprint can control, honestly stated rather than glossed over. |

## R-18 — Stakeholder Consultation Schedule Overrun

| Situation | Consultation across seven geographically distinct states and the FCT, within a nominal two-week window, is the single most schedule-compressed activity in the entire twelve-week engagement. |
| --- | --- |
| Potential Impact | Because WP1 sits at the head of the critical path (Section 13.5), any overrun here does not stay contained — it propagates through Governance Charter adoption, platform configuration, migration, and every subsequent work package. |
| Mitigation | WP1 begins on day one without a lead-in delay; consultation logistics (travel, scheduling with seven distinct state administrations) are planned ahead of contract signature wherever the procurement process allows; the Executive Advice Briefing's own recommendation to present a realistic, not idealized, account of this specific schedule risk is followed rather than understated. |
| Residual Risk | Accepted as Medium-High: this is the one risk in the entire register most directly outside the consultant's unilateral control, since it depends on seven separate state administrations' own availability and responsiveness. |

# 14.12 Risk Monitoring and Review

Every risk in this register is entered into the Risk Register functional module (Section 4.4) at engagement start and tracked through the same lifecycle used for all programme risks (Section 2.5): Identify → Assess → Mitigate → Monitor → Close. Risk review is not a separate governance activity — it is folded into the existing governance cadence (Section 12.8): Critical and High impact risks are reviewed at every Enterprise Architecture Review Board milestone meeting; the full register is reviewed at the annual Governance Charter renewal review; and any risk that materializes into an actual incident is handled through the Incident Response process (Section 8.9), with the register updated to reflect lessons learned.

# 14.13 Transition to Section 15

Section 15 (Architecture Review Report) performs the quality-assurance pass the governing prompt itself requires before this Blueprint is finalized — reviewing the entire architecture, challenging assumptions, identifying weaknesses and missing components, and confirming that every risk in this register has a proportionate, honestly stated mitigation rather than an overstated one.