SAPZ MASTER ENGINEERING KNOWLEDGE BASE

Part 5

Engineering Work Packages 01–05

Enterprise System Management (ESM) Platform &

Central Knowledge Repository (CKR)

Special Agro-Industrial Processing Zones (SAPZ) Programme

Federal Republic of Nigeria

Master Engineering Knowledge Base (MEKB) — Bridging Documentation and Implementation

PART 5

Engineering Work Packages 01–05

Part Overview

This Part specifies the first five Engineering Work Packages — WP-01 through WP-05 — the platform's foundational database, API, DevSecOps, administration, and security capability, per the WBS allocation established in Part 4, Section 4.6. Each Work Package is written to be independently implementable by Antigravity: self-contained, fully traceable to its governing documents, and bounded by an explicit Definition of Ready and Definition of Done.

These five Work Packages are foundational — every one of the remaining twenty Work Packages in Parts 6 through 8 depends on WP-01, WP-02, and WP-03 being complete, and most depend on WP-04 and WP-05 for authenticated, access-controlled operation.

GOVERNANCE NOTE Work Package scope, numbering, and sequencing are fixed as of Part 4 and are not altered here. Any field below that appears to introduce new scope beyond what is defined in the referenced governing documents is a documentation defect and shall be raised as a Change Request, not silently implemented.

# 5.1  WP-01 — Platform Database Foundation

| Field | Detail |
| --- | --- |
| Objective | Stand up the platform's complete physical database schema, migration framework, indexing strategy, and audit/data-governance foundation before any module-specific Work Package begins. |
| Business Context | Every one of the twenty functional modules depends on a stable, correctly indexed, audited database layer. Sequencing this work first eliminates rework across all downstream Work Packages. |
| Scope | Full physical schema implementation per DDS Parts 3–4; migration framework and versioning; baseline indexing per DDS Part 8; constraint enforcement per DDS Part 9; audit logging framework per DDS Part 10; master/lookup data seeding per DDS Part 6–7. |
| Out of Scope | Module-specific entity refinement beyond the DDS baseline (delivered within each module's own Work Package); reporting data marts (WP-17); AI/search indexing (WP-13, WP-15). |
| Inputs | DDS Parts 1–11, Data Dictionary (DDS Part 4), Enterprise Solution Architecture Section 06. |
| Outputs | A deployed, migrated, indexed, audited database instance in the development environment, ready for all subsequent Work Packages. |
| Dependencies | None — first Work Package in the sequence. Blocks WP-04 through WP-23. |

User Stories

- US-001: As a Backend Engineer, I want a stable database schema so that I can build service logic against fixed table structures.

- US-002: As a Data Architect, I want a migration framework so that schema changes are versioned and reversible.

- US-003: As a Compliance Officer, I want every data change audited so that the platform can withstand an IFAD audit.

Functional Requirements

- FR-DB-01: Implement all entities defined in DDS Part 3 (Entity Catalogue).

- FR-DB-02: Implement all field-level constraints defined in DDS Part 9.

- FR-DB-03: Implement audit logging for create, update, and delete operations on all entities, per DDS Part 10.

- FR-DB-04: Seed all master and lookup data defined in DDS Part 6 and Part 7.

Non-Functional Requirements

- NFR-DB-01: All indexed queries return within the performance thresholds defined in DDS Part 16.

- NFR-DB-02: Migrations execute with zero data loss and are fully reversible.

- NFR-DB-03: Backup and recovery procedures validated per DDS Part 15.

Database Entities

All entities defined in DDS Part 3 (Entity Catalogue) — the full schema baseline consumed by every subsequent Work Package.

API Endpoints

| Method / Path | Description |
| --- | --- |
| None | Database layer only; consumed internally by all Backend Engineering services from WP-04 onward. |

UI Screens

- None — infrastructure Work Package.

Security Controls

- Encryption at rest for all sensitive fields per DDS Part 11.

- Row-level security scaffolding for future module-level access control (completed in WP-05).

- Database credential management via the DevSecOps secrets vault (WP-03).

Acceptance Criteria

1. All DDS Part 3 entities exist in the target schema with correct types and constraints.

2. Migration framework successfully applies and rolls back a test migration.

3. Audit log captures 100% of create/update/delete operations in a test suite.

4. All master/lookup data seeded and validated against DDS Part 6/7.

Test Cases

| Test ID | Type | Description |
| --- | --- | --- |
| UT-DB-01 | Unit | Constraint enforcement rejects invalid data. |
| IT-DB-01 | Integration | Migration up/down cycle preserves data integrity. |
| ST-DB-01 | Security | Encrypted fields are not readable in plaintext at rest. |
| PT-DB-01 | Performance | Baseline query set meets DDS Part 16 thresholds. |

Documentation Updates

- DDS Part 1 (Executive Database Overview) status updated to ‘Implemented’.

- Repository /docs/database/ populated per Appendix O, Section O.9.

Related ADRs

- ADR-0001: Database Platform Selection.

- ADR-0002: Migration Framework Selection.

Risks

| Risk ID | Description | Mitigation |
| --- | --- | --- |
| R-DB-01 | Schema rework if module-level requirements surface gaps in DDS. | Module Work Package review gate required before implementation begins. |

Deliverables

- DEL-ENG-001: Deployed Database Schema.

- DEL-ENG-002: Migration Framework.

- DEL-ENG-003: Audit Logging Framework.

| Gate | Criteria |
| --- | --- |
| Definition of Ready | DDS Parts 1–11 approved and baselined; development environment provisioned (WP-03 in progress or complete). |
| Definition of Done | All acceptance criteria met; test cases passing; ADRs recorded; documentation updated; Technical Lead and Data Architect sign-off per Appendix O, Section O.6. |

# 5.2  WP-02 — API & Integration Platform Foundation

| Field | Detail |
| --- | --- |
| Objective | Stand up the platform's API gateway, OpenAPI contract framework, authentication/authorization scaffolding at the API layer, and external integration adapters before module-specific API development begins. |
| Business Context | All twenty modules expose functionality through a consistent API layer. Establishing gateway, versioning, and contract standards first prevents inconsistent endpoint design across modules. |
| Scope | API Gateway configuration; OpenAPI 3.1 contract framework per AIDS Part 17; base authentication/authorization middleware per AIDS Part 5; error handling framework per AIDS Part 7; webhook dispatch framework per AIDS Part 8; external integration adapter scaffolding per AIDS Part 9. |
| Out of Scope | Module-specific endpoint implementation (delivered within each module's Work Package); AI/search-specific APIs (WP-13, WP-15, WP-23). |
| Inputs | AIDS Parts 1–19, SRS Parts 28–29. |
| Outputs | A running API gateway with authentication middleware, versioning strategy, and a published base OpenAPI specification, ready for module endpoints to be registered. |
| Dependencies | WP-01 (Database Foundation, for entity-aligned contracts). Blocks WP-04 through WP-23. |

User Stories

- US-004: As a Backend Engineer, I want a consistent API gateway so that every module's endpoints follow the same authentication and versioning pattern.

- US-005: As an external integration partner, I want a published OpenAPI specification so that I can build against a stable contract.

- US-006: As a Security Architect, I want centralized authentication middleware so that authorization logic is not duplicated per module.

Functional Requirements

- FR-API-01: Implement API Gateway routing and versioning strategy per AIDS Part 2.

- FR-API-02: Implement OAuth 2.0 / JWT authentication middleware per AIDS Part 5.

- FR-API-03: Implement standardized error response format per AIDS Part 7.

- FR-API-04: Implement webhook dispatch framework per AIDS Part 8.

Non-Functional Requirements

- NFR-API-01: API Gateway adds no more than the latency budget defined in AIDS Part 13.

- NFR-API-02: Authentication middleware supports the concurrent session volume defined in SRS Part 33.

- NFR-API-03: All endpoints conform to the OpenAPI 3.1 Blueprint (AIDS Part 17).

Database Entities

api_clients, api_tokens, webhook_subscriptions — consuming the core schema established in WP-01.

API Endpoints

| Method / Path | Description |
| --- | --- |
| POST /api/v1/auth/token | Issue an access token for an authenticated client. |
| POST /api/v1/auth/refresh | Refresh an expiring access token. |
| GET /api/v1/health | Platform health check endpoint. |
| POST /api/v1/webhooks/subscriptions | Register a webhook subscription. |

UI Screens

- None — infrastructure Work Package. API Client Management screen delivered under WP-04 (Administration).

Security Controls

- TLS termination at the gateway.

- Rate limiting on all public-facing endpoints.

- JWT signature validation on every protected request.

- API key rotation policy per AIDS Part 14.

Acceptance Criteria

1. Gateway successfully routes to a test service with authentication enforced.

2. OpenAPI specification validates against the AIDS Part 17 blueprint.

3. Webhook dispatch successfully delivers a test event with retry on failure.

4. Error responses conform to the standardized format for 100% of test cases.

Test Cases

| Test ID | Type | Description |
| --- | --- | --- |
| UT-API-01 | Unit | Token validation rejects expired or malformed JWTs. |
| IT-API-01 | Integration | Gateway routes an authenticated request to a backend service. |
| ST-API-01 | Security | Unauthenticated request to a protected endpoint returns 401. |
| PT-API-01 | Performance | Gateway overhead remains within the AIDS Part 13 budget under load. |

Documentation Updates

- AIDS Part 17 (OpenAPI Blueprint) status updated to ‘Implemented’.

- Repository /docs/api/ populated.

Related ADRs

- ADR-0003: API Gateway Platform Selection.

- ADR-0004: Authentication Strategy.

Risks

| Risk ID | Description | Mitigation |
| --- | --- | --- |
| R-API-01 | Gateway becomes a single point of failure. | High-availability gateway configuration delivered under WP-03. |

Deliverables

- DEL-ENG-004: API Gateway Configuration.

- DEL-ENG-005: Base OpenAPI Specification.

- DEL-ENG-006: Authentication Middleware.

| Gate | Criteria |
| --- | --- |
| Definition of Ready | WP-01 complete or entity contracts stable; AIDS Parts 1–19 approved. |
| Definition of Done | All acceptance criteria met; test cases passing; ADRs recorded; documentation updated; Backend Lead and Solution Architect sign-off. |

# 5.3  WP-03 — DevSecOps Pipeline & Environment Foundation

| Field | Detail |
| --- | --- |
| Objective | Establish CI/CD pipelines, environment provisioning, secrets management, and baseline observability before any module code is built or deployed. |
| Business Context | A reliable pipeline and environment strategy is the precondition for every subsequent Work Package to be built, tested, and deployed consistently. |
| Scope | CI/CD pipeline configuration per PDIB Part 14; environment provisioning (dev, staging, production) per PDIB Part 13; secrets vault; baseline monitoring/alerting per PDIB Part 15; backup and DR scaffolding per DDS Part 15 and PDIB Part 16. |
| Out of Scope | Module-specific deployment configuration (delivered within each module Work Package); full hypercare monitoring dashboards (WP-24 closeout). |
| Inputs | PDIB Parts 13–17, Appendix M (Environment & Release Matrix). |
| Outputs | A working CI/CD pipeline capable of building, testing, and deploying a sample service to each environment, with secrets management and baseline monitoring active. |
| Dependencies | None — runs in parallel with WP-01/WP-02. Blocks all module Work Packages' deployment activities. |

User Stories

- US-007: As a DevSecOps Lead, I want an automated CI/CD pipeline so that every merged change is built, tested, and deployable without manual steps.

- US-008: As a Security Architect, I want centralized secrets management so that credentials are never hard-coded.

- US-009: As an Operations Lead, I want baseline monitoring so that I can detect service degradation before users report it.

Functional Requirements

- FR-DEVOPS-01: Implement CI pipeline stages — build, unit test, security scan, package — per PDIB Part 14.

- FR-DEVOPS-02: Implement CD pipeline stages — deploy to staging, run integration tests, promote to production — per PDIB Part 14.

- FR-DEVOPS-03: Implement environment configuration management across dev, staging, and production per PDIB Part 13.

- FR-DEVOPS-04: Implement secrets vault integration for all services.

Non-Functional Requirements

- NFR-DEVOPS-01: Pipeline build-to-deploy cycle time within the target defined in PDIB Part 14.

- NFR-DEVOPS-02: Monitoring alerts fire within the SLA defined in PDIB Part 15.

- NFR-DEVOPS-03: Disaster recovery procedures meet the RTO/RPO targets in DDS Part 15.

Database Entities

None directly — infrastructure Work Package. Pipeline run and deployment logs are stored in operational tooling, not the application schema.

API Endpoints

| Method / Path | Description |
| --- | --- |
| None | Infrastructure Work Package — pipeline and monitoring tooling operate outside the application API surface. |

UI Screens

- None — pipeline dashboards are provided by DevSecOps tooling, not the application.

Security Controls

- Secrets never stored in source control.

- Pipeline security scanning gate (SAST / dependency scanning) per Handbook Chapter 15.

- Production deployment requires DevSecOps Lead approval.

Acceptance Criteria

1. A sample service builds, tests, and deploys through all three environments via the pipeline.

2. Secrets vault successfully injects credentials at runtime with no plaintext exposure.

3. A simulated service degradation triggers a monitoring alert within SLA.

4. A backup/restore cycle is successfully validated in the staging environment.

Test Cases

| Test ID | Type | Description |
| --- | --- | --- |
| IT-DEVOPS-01 | Integration | End-to-end pipeline run from commit to production deployment. |
| ST-DEVOPS-01 | Security | Pipeline fails the build when a known-vulnerable dependency is introduced. |
| PT-DEVOPS-01 | Performance | Pipeline cycle time meets the PDIB Part 14 target. |

Documentation Updates

- PDIB Part 13 and Part 14 status updated to ‘Implemented’.

- Repository /docs/devsecops/ populated.

Related ADRs

- ADR-0005: CI/CD Platform Selection.

- ADR-0006: Secrets Management Strategy.

Risks

| Risk ID | Description | Mitigation |
| --- | --- | --- |
| R-DEVOPS-01 | Environment drift between staging and production. | Infrastructure-as-code enforcement across all environments. |

Deliverables

- DEL-ENG-007: CI/CD Pipeline.

- DEL-ENG-008: Environment Configuration.

- DEL-ENG-009: Secrets Vault Integration.

- DEL-ENG-010: Baseline Monitoring Configuration.

| Gate | Criteria |
| --- | --- |
| Definition of Ready | PDIB Parts 13–17 approved; target cloud/hosting platform selected. |
| Definition of Done | All acceptance criteria met; test cases passing; ADRs recorded; documentation updated; DevSecOps Lead and Security Architect sign-off. |

# 5.4  WP-04 — Administration & User Management

| Field | Detail |
| --- | --- |
| Objective | Deliver the Administration module — user provisioning, organizational structure management, system configuration — as the first module-level Work Package, enabling all subsequent modules to operate against real users and organizational data. |
| Business Context | Every module requires authenticated users and organizational context (zones, roles). Administration must exist before meaningful module-level testing can occur. |
| Scope | User provisioning and lifecycle; organizational unit management; system configuration store; feature toggle framework; per SRS Part 10. |
| Out of Scope | Role/permission definition logic itself (delivered in WP-05); training records (WP-19). |
| Inputs | SRS Part 10; DDS entities from WP-01; API scaffolding from WP-02. |
| Outputs | A functioning Administration module allowing user and organizational data to be created and managed. |
| Dependencies | WP-01 (database), WP-02 (API), WP-03 (deployment). Blocks WP-05 and all subsequent module Work Packages requiring authenticated users. |

User Stories

- US-010: As a Super Administrator, I want to provision new users so that staff can access the platform.

- US-011: As a Super Administrator, I want to manage organizational units (zones) so that data can be scoped correctly.

- US-012: As a Programme Manager, I want to configure system settings so that the platform reflects programme-specific parameters.

Functional Requirements

- FR-ADM-01: Implement user CRUD and lifecycle states (active, suspended, deactivated) per SRS Part 10.

- FR-ADM-02: Implement organizational unit hierarchy management.

- FR-ADM-03: Implement system configuration store with audit history.

- FR-ADM-04: Implement feature toggle framework.

Non-Functional Requirements

- NFR-ADM-01: User provisioning actions complete within the response time defined in SRS Part 33.

- NFR-ADM-02: All configuration changes are audited and attributable to a user.

Database Entities

users, organizational_units, system_configuration (DDS Part 3).

API Endpoints

| Method / Path | Description |
| --- | --- |
| POST /api/v1/admin/users | Create a new user. |
| GET /api/v1/admin/users/{id} | Retrieve a user record. |
| PATCH /api/v1/admin/users/{id} | Update a user's status or attributes. |
| GET /api/v1/admin/config | Retrieve system configuration. |
| PATCH /api/v1/admin/config | Update system configuration. |

UI Screens

- Admin Console

- User Management screen

- Organizational Unit Manager

- System Settings panel (SRS Part 23).

Security Controls

- Super-admin tier RBAC, coordinated with WP-05.

- Configuration change audit log.

- Dual control required for Super Admin role assignment.

Acceptance Criteria

1. A Super Administrator can create, update, suspend, and deactivate a user.

2. Organizational units can be created in a hierarchy and assigned to users.

3. System configuration changes are visible in an audit log with actor and timestamp.

4. Feature toggles can be enabled or disabled without a deployment.

Test Cases

| Test ID | Type | Description |
| --- | --- | --- |
| UT-ADM-01 | Unit | User lifecycle state transitions enforce valid state machine rules. |
| IT-ADM-01 | Integration | User creation triggers correct organizational unit assignment. |
| UAT-ADM-01 | UAT | Super Administrator completes full user provisioning workflow in staging. |

Documentation Updates

- SRS Part 10 status updated to ‘Implemented’.

- User Guide section for Administration drafted.

Related ADRs

- ADR-0007: Organizational Hierarchy Model.

Risks

| Risk ID | Description | Mitigation |
| --- | --- | --- |
| R-ADM-01 | Organizational hierarchy changes after go-live could require data migration. | Flexible hierarchy model validated in this Work Package. |

Deliverables

- DEL-ENG-011: Administration Module.

- DEL-ENG-012: Admin Console UI.

| Gate | Criteria |
| --- | --- |
| Definition of Ready | WP-01, WP-02, WP-03 complete; SRS Part 10 approved. |
| Definition of Done | All acceptance criteria met; test cases passing including UAT; ADR recorded; documentation updated; Technical Lead and Product Owner sign-off. |

# 5.5  WP-05 — Security & Access Control

| Field | Detail |
| --- | --- |
| Objective | Deliver the Security (Module-Level) capability — role and permission management, session management, access audit — completing the platform's core RBAC enforcement layer. |
| Business Context | No module can enforce least-privilege access until roles and permissions are defined and enforceable. This Work Package completes the security foundation alongside WP-04. |
| Scope | Role and permission management; access control list enforcement; session management; access audit viewer; per SRS Part 9 and the Security Architecture. |
| Out of Scope | Module-specific business rule authorization (delivered within each module Work Package, consuming this RBAC layer); AI Assistant-specific access controls (WP-23). |
| Inputs | SRS Part 9; Security Architecture (EA Blueprint Part 9 / EA Blueprint 2.0 Section 08); Appendix K. |
| Outputs | A fully functioning RBAC system enforced across the API gateway and application services. |
| Dependencies | WP-01, WP-02, WP-03, WP-04 (organizational context for role scoping). Blocks all subsequent module Work Packages' security control validation. |

User Stories

- US-013: As a Security Architect, I want centrally defined roles and permissions so that access control is consistent across all modules.

- US-014: As an Administrator, I want to assign roles to users so that they receive only the access they need.

- US-015: As an Auditor, I want an access audit trail so that I can verify least-privilege compliance.

Functional Requirements

- FR-SEC-01: Implement role and permission CRUD per SRS Part 9.

- FR-SEC-02: Implement role assignment with organizational scoping (zone-level, project-level).

- FR-SEC-03: Implement session management including timeout and forced logout.

- FR-SEC-04: Implement access audit logging and viewer.

Non-Functional Requirements

- NFR-SEC-01: Permission checks add no more than the latency budget defined in AIDS Part 13.

- NFR-SEC-02: MFA supported for all Administrator and Executive-tier roles.

- NFR-SEC-03: 100% of access control decisions are logged, per Appendix K.

Database Entities

roles, permissions, role_assignments, sessions, access_audit_log (DDS Part 11).

API Endpoints

| Method / Path | Description |
| --- | --- |
| POST /api/v1/roles | Create a new role. |
| GET /api/v1/permissions | List available permissions. |
| POST /api/v1/roles/{id}/assign | Assign a role to a user. |
| GET /api/v1/sessions | List active sessions. |
| DELETE /api/v1/sessions/{id} | Terminate a session. |

UI Screens

- Role Management screen

- Permission Matrix editor

- Session Management screen

- Access Audit Viewer (SRS Part 23).

Security Controls

- Least-privilege enforcement across all roles.

- MFA configuration for Administrator and Executive-tier roles.

- Session timeout enforcement.

- Full access audit trail per Appendix K (Security Controls & Compliance Matrix).

Acceptance Criteria

1. A new role with a defined permission set can be created and assigned to a user.

2. A user without the required permission is denied access to a protected action, verified end-to-end through the API gateway.

3. Session timeout correctly forces re-authentication after the configured period.

4. Access audit log captures 100% of access control decisions in a test suite.

Test Cases

| Test ID | Type | Description |
| --- | --- | --- |
| UT-SEC-01 | Unit | Permission evaluation logic correctly resolves role-based access. |
| IT-SEC-01 | Integration | API gateway enforces the RBAC decision returned by the Security module. |
| ST-SEC-01 | Security | Privilege escalation attempt is blocked and logged. |
| UAT-SEC-01 | UAT | Administrator completes full role assignment and verification workflow. |

Documentation Updates

- SRS Part 9 and SRS Part 32 status updated to ‘Implemented’.

- Security Controls Matrix (Appendix K) cross-referenced with implementation evidence.

Related ADRs

- ADR-0008: RBAC Model — Role-Based vs. Attribute-Based.

- ADR-0009: Session Management Strategy.

Risks

| Risk ID | Description | Mitigation |
| --- | --- | --- |
| R-SEC-01 | Overly coarse-grained roles could force privilege creep. | Granular permission model validated against SRS Part 9. |

Deliverables

- DEL-ENG-013: Security & RBAC Module.

- DEL-ENG-014: Access Audit Viewer.

| Gate | Criteria |
| --- | --- |
| Definition of Ready | WP-01 through WP-04 complete; Security Architecture and SRS Part 9 approved. |
| Definition of Done | All acceptance criteria met; test cases passing including UAT; ADRs recorded; documentation and Security Controls Matrix updated; Security Architect and Steering Committee sign-off per Appendix O, Section O.6. |

# 5.6  Summary and Bridge to Part 6

This Part fully specified the five foundational Engineering Work Packages that must be complete before any other module Work Package can begin implementation: Platform Database Foundation, API & Integration Platform Foundation, DevSecOps Pipeline & Environment Foundation, Administration & User Management, and Security & Access Control.

Part 6 specifies Work Packages 06 through 10 — Executive Management, Programme Management, Projects, Tasks, and Workflow Engine — the first wave of module-level Work Packages, each built directly on top of the foundation established here.

## 5.6.1  Key Takeaways

- WP-01 through WP-03 have no dependencies on each other and can be executed in parallel; WP-04 and WP-05 depend on all three.

- Every Work Package carries the full field set required by the MEKB: objective through Definition of Done, with zero fields left unspecified.

- Nine new ADRs (ADR-0001 through ADR-0009) are anticipated from this wave of Work Packages alone.

- WP-04 and WP-05 together complete the platform's authentication, authorization, and organizational-context foundation required by all twenty remaining Work Packages.

## 5.6.2  Related Parts

- MEKB Part 4 — Engineering Work Breakdown Structure

- MEKB Part 6 — Engineering Work Packages 06–10

- MEKB Part 9 — Sprint Roadmap

- MEKB Part 10 — Work Package Dependency Matrix and Master Prompt Library