SAPZ MASTER ENGINEERING KNOWLEDGE BASE

Part 11

Work Package Dependency Matrix

Enterprise System Management (ESM) Platform &

Central Knowledge Repository (CKR)

Special Agro-Industrial Processing Zones (SAPZ) Programme

Federal Republic of Nigeria

Master Engineering Knowledge Base (MEKB) — Bridging Documentation and Implementation

PART 11

Work Package Dependency Matrix

Part Overview

This Part shows, for every one of the twenty-five Engineering Work Packages, what it depends on, what it enables, and the risk to the programme if it is delayed — and identifies the programme's critical path. No new dependency is introduced here: every relationship below is derived directly from the Dependencies field already fixed in each Work Package's specification (MEKB Parts 5–8).

# 11.1  Purpose and How to Use This Matrix

| Purpose | Provide a single, complete forward and backward dependency view across all twenty-five Work Packages. |
| --- | --- |
| Business Value | The primary reference for schedule risk management — answers 'what happens if this Work Package slips' for any Work Package in the programme. |
| Engineering Perspective | Depends On is the forward view (what must finish first); Enables is the backward view (what is waiting on this Work Package). |
| Expected Outcome | A Programme Manager can identify schedule risk from this matrix alone, without cross-referencing all twenty-five Work Package specifications. |

# 11.2  Work Package Dependency Matrix

| WP | Depends On | Enables | Risk if Delayed |
| --- | --- | --- | --- |
| WP-01 | None | WP-02, WP-04, WP-05 (and transitively all Work Packages through WP-23) | Delays the start of nearly the entire programme; all module Work Packages blocked. |
| WP-02 | WP-01 | WP-04 onward (every module's API layer) | Blocks all module-level API development; DevSecOps pipeline testing constrained. |
| WP-03 | None (parallel to WP-01/02) | WP-04 onward (deployment path for every module); WP-14 (CDN) | No module can be deployed or tested in staging/production; delays Sprint 3 onward. |
| WP-04 | WP-01, WP-02, WP-03 | WP-05, WP-10, WP-19; all authenticated module testing | Blocks Security (WP-05) and the Workflow Engine (WP-10); delays Sprint 4 onward. |
| WP-05 | WP-01–04 | WP-06 onward (every module's access control); WP-12, WP-14, WP-15, WP-23 | No module can enforce least-privilege access; blocks nearly the entire remaining programme. |
| WP-06 | WP-01–05 (WP-07 mocked) | None downstream — a leaf, consumer-only Work Package | Executive visibility delayed; no cascading schedule impact on other Work Packages. |
| WP-07 | WP-01–05 | WP-06 (data), WP-08, WP-16, WP-22 | Blocks Projects (WP-08) and the entire Core Delivery Chain; high schedule impact. |
| WP-08 | WP-07 | WP-09, WP-16 | Blocks Tasks (WP-09) and the Workflow Engine chain. |
| WP-09 | WP-08 | WP-10, WP-18 | Blocks the Workflow Engine (WP-10), the single highest fan-out Work Package in the programme. |
| WP-10 | WP-04, WP-09 | WP-11, WP-18, WP-20 | Blocks Approvals, Notifications, and Support — the programme's process-orchestration backbone. |
| WP-11 | WP-10, WP-04 | WP-12, WP-18, WP-22 | Blocks Documents' release gating and the Public Portal's publish workflow. |
| WP-12 | WP-05, WP-11 | WP-13, WP-15, WP-19, WP-22 | Blocks Knowledge Repository and Search — the entire content and discovery chain. |
| WP-13 | WP-12 | WP-15, WP-21, WP-23 | Blocks Search and the AI Assistant, the programme's Phase 2 differentiator. |
| WP-14 | WP-03, WP-05 | None downstream | Media content delayed; no cascading schedule impact. |
| WP-15 | WP-12, WP-13, WP-05 | WP-23 | Blocks the AI Assistant (WP-23), the final capability before release certification. |
| WP-16 | WP-07, WP-08 | WP-17 | Blocks Analytics (WP-17); moderate schedule impact. |
| WP-17 | WP-16 | None downstream | Executive trend insight delayed; no cascading schedule impact. |
| WP-18 | WP-09, WP-10, WP-11 | WP-20 | Blocks Support's SLA escalation notifications. |
| WP-19 | WP-04, WP-12 | None downstream | Training rollout delayed; no cascading schedule impact. |
| WP-20 | WP-18, WP-10 | WP-21 | Blocks Help Desk's ticket-deflection measurement. |
| WP-21 | WP-13, WP-20 | None downstream | Self-service deflection delayed; Support ticket volume may run higher than planned. |
| WP-22 | WP-07, WP-11, WP-12 | None downstream (gates the Sprint 16 milestone) | Delays the 'All Phase 1 Functional Modules Complete' milestone and, transitively, WP-23 through WP-25. |
| WP-23 | WP-13, WP-15, WP-05 | WP-24 | Blocks WP-24 per its fixed Definition of Ready, delaying go-live directly. |
| WP-24 | WP-01–23 (all) | WP-25 | Directly delays go-live; the most schedule-critical Work Package after the Foundation wave. |
| WP-25 | WP-01–24 (all) | None — final Work Package | Directly delays Project Closure and final donor/government acceptance. |

# 11.3  Critical Path

| Purpose | Identify the longest chain of dependent Work Packages that determines the minimum possible programme duration. |
| --- | --- |
| Business Value | Tells the Programme Manager exactly which Work Packages must never slip without the entire go-live date moving. |
| Engineering Perspective | Derived by tracing the longest unbroken Depends-On chain from WP-01 through WP-25. |
| Expected Outcome | Unambiguous identification of the fifteen schedule-critical Work Packages, and the nine 'near-critical' Work Packages that carry limited float. |

The programme's critical path — the longest chain of dependent Work Packages, any delay to which delays the entire programme — runs as follows:

WP-01 → WP-02 → WP-04 → WP-05 → WP-07 → WP-08 → WP-09 → WP-10 → WP-11 → WP-12 → WP-13 → WP-15 → WP-23 → WP-24 → WP-25 Sprint: 1 2 3 4 5 6 7 8 9 10 11 12 17 18 19

This fifteen-Work-Package chain spans the full twenty-sprint roadmap, from Sprint 1 through Sprint 19. Work Packages WP-06, WP-14, WP-16 through WP-22 sit off the critical path and carry schedule float between Sprint 5 and Sprint 16 — but because WP-24's Definition of Ready requires WP-01 through WP-23 to be complete, none of these 'near-critical' Work Packages may slip past the end of Sprint 17 without delaying WP-24, and therefore go-live.

RISK WP-10 (Workflow Engine) and WP-12 (Documents) are the two highest fan-out nodes on the critical path — each directly enables three or more downstream Work Packages. Schedule risk on the critical path should be monitored most closely at these two points.

## 11.3.1  Highest Fan-Out Work Packages

The following Work Packages carry the greatest schedule risk if delayed, measured by the number of Work Packages directly or transitively blocked:

| Work Package | Fan-Out |
| --- | --- |
| WP-01 | 3 direct (WP-02, WP-04, WP-05); ~22 transitive |
| WP-05 | 4 direct (WP-06– chain, WP-12, WP-14, WP-15, WP-23) |
| WP-10 | 3 direct (WP-11, WP-18, WP-20) |
| WP-12 | 4 direct (WP-13, WP-15, WP-19, WP-22) |

# 11.4  Summary and Bridge to Part 12

This Part mapped the complete forward and backward dependency structure across all twenty-five Work Packages and identified the fifteen-Work-Package critical path spanning Sprint 1 through Sprint 19, together with the highest fan-out risk points.

Part 12 — Master Prompt Library — provides the reusable prompt template Antigravity uses to execute any Work Package identified in this dependency matrix, from architecture review through Definition of Done validation.

## 11.4.1  Key Takeaways

- Fifteen of twenty-five Work Packages sit on the critical path; the remaining ten carry float but must still complete before WP-24 begins.

- WP-10 and WP-12 are the highest fan-out Work Packages on the critical path and warrant the closest schedule monitoring.

- WP-24 and WP-25's dependency on 'all prior Work Packages' means the critical path effectively absorbs every near-critical Work Package by Sprint 17.

## 11.4.2  Related Parts

- MEKB Part 4 — Engineering Work Breakdown Structure

- MEKB Part 9 — Sprint Roadmap

- MEKB Part 10 — Master Product Backlog

- MEKB Part 12 — Master Prompt Library