VOLUME IV — ENTERPRISE ENGINEERING WORK PACKAGE LIBRARY (EWPL)

Part 2

Master Work Package Catalogue

Enterprise System Management (ESM) Platform &

Central Knowledge Repository (CKR)

Special Agro-Industrial Processing Zones (SAPZ) Programme

Federal Republic of Nigeria

Portfolio Dashboard — All 25 Engineering Work Packages at a Glance

PART 2

Master Work Package Catalogue

# 2.1  Portfolio Summary

| Purpose | Give a single-page portfolio view of the entire twenty-five Work Package library before the detail tables. |
| --- | --- |
| Business Value | Lets Programme Management answer 'how big is this, and how far along is it' without opening any individual Work Package. |
| Engineering Perspective | Figures are derived directly from the twenty-five Work Package entries that follow, which in turn preserve the WP-01–25 identifiers fixed in MEKB Parts 4–8. |
| Expected Outcome | A portfolio-level dashboard suitable for a Steering Committee status report. |

| Metric | Value |
| --- | --- |
| Total Work Packages | 25 (WP-01 through WP-25) |
| Total Estimated Story Points (WP-level re-estimate) | 382 points |
| Complexity Mix | High: 9 ¦ Medium: 10 ¦ Low: 6 |
| Business Priority Mix | Critical: 11 ¦ High: 8 ¦ Medium: 6 |
| Work Packages Ready for Sprint Entry | 5 (WP-01 through WP-05 — Definition of Ready met) |
| Work Packages Defined, Pending Sprint Scheduling | 20 (WP-06 through WP-25) |
| Releases Spanned | 5 (ERS Release 1 through Release 5) |
| Sprints Spanned | 20 (Sprint 0 through Sprint 19, per MEKB Part 9) |

TRACEABILITY Every figure in this Part is derived from, and fully consistent with, MEKB Parts 4-11, the Master Product Backlog (MEKB Part 10), and the Enterprise Release Strategy (ERS) Parts 1-2. No Work Package identifier, dependency, or release assignment in this catalogue differs from those governing sources.

# 2.2  Table A — Identity & Scope

Every Work Package's identity, business capability, and strategic objective.

| WP | Title | Business Capability | Strategic Objective |
| --- | --- | --- | --- |
| WP-01 | Platform Database Foundation | Platform Data Backbone | Establish the single, secure, auditable system of record every module reads and writes through. |
| WP-02 | API & Integration Platform Foundation | Platform Integration Backbone | Establish the single gateway and contract pattern every module exposes itself through. |
| WP-03 | DevSecOps Pipeline & Environment Foundation | Build & Release Automation | Establish CI/CD, environments, and security scanning so nothing else can be tested or deployed without it. |
| WP-04 | Administration & User Management | Platform Administration | Give the platform real users, roles, and organizational context to build and test every later module against. |
| WP-05 | Security & Access Control | Access Governance | Enforce least-privilege access before any module exposes real business data. |
| WP-06 | Executive Management | Executive Visibility | Give leadership a live view of programme health as soon as real data exists. |
| WP-07 | Programme Management | Programme Delivery Chain | Establish the top-level organizing entity every project and zone is scoped within. |
| WP-08 | Projects | Project Delivery | Give programmes a structured, trackable set of projects. |
| WP-09 | Tasks | Work Execution | Break projects into assignable, trackable units of work. |
| WP-10 | Workflow Engine | Process Orchestration | Provide the shared orchestration layer every approval-style process runs on. |
| WP-11 | Approvals | Governance & Sign-off | Prove the workflow pattern on its first and most demanding consumer. |
| WP-12 | Documents | Enterprise Content Management | Establish the platform's document system of record. |
| WP-13 | Knowledge Repository | Organizational Knowledge | Organize what Documents stores into curated, discoverable knowledge. |
| WP-14 | Media | Media Management | Provide independent media handling in parallel with Documents. |
| WP-15 | Search (Platform-Wide) | Enterprise Discovery | Index Documents and Knowledge Repository into unified, semantic search. |
| WP-16 | Reporting | Business Reporting | Report on real Programme and Project data. |
| WP-17 | Analytics | Business Intelligence | Build on Reporting's data access into trend and comparative analytics. |
| WP-18 | Notifications (Platform-Wide) | Platform Communication | Dispatch events already being produced by Tasks, Workflow, and Approvals. |
| WP-19 | Training | User Enablement | Deliver courses using real user records and a content store. |
| WP-20 | Support | User Support | Escalate tickets using Notifications and Workflow. |
| WP-21 | Help Desk | Self-Service Support | Deflect tickets from Support using Knowledge Repository content. |
| WP-22 | Public Portal | External Transparency | Publish Approvals-gated Programme and Document content externally. |
| WP-23 | AI Assistant | Intelligent Assistance | Retrieve from a stable, indexed knowledge base via conversational AI. |
| WP-24 | Quality Engineering & Release Readiness | Platform Quality Assurance | Perform the full-platform inspection before General Availability. |
| WP-25 | Documentation, ADR & Traceability Closeout | Programme Documentation | Close out the handover binder the inspection (WP-24) confirmed accurate. |

# 2.3  Table B — Delivery Coordinates

Every Work Package's release, sprint, size, and priority.

| WP | Release | Sprint | Pts | Complexity | Biz Priority | Tech Priority |
| --- | --- | --- | --- | --- | --- | --- |
| WP-01 | ERS Release 1 | Sprint 1 | 21 | High | Critical | Critical |
| WP-02 | ERS Release 1 | Sprint 2 | 21 | High | Critical | Critical |
| WP-03 | ERS Release 1 | Sprint 2 | 18 | High | Critical | Critical |
| WP-04 | ERS Release 1 | Sprint 3 | 21 | Medium | Critical | High |
| WP-05 | ERS Release 1 | Sprint 4 | 21 | High | Critical | Critical |
| WP-06 | ERS R1 (thin) / R4 (full) | Sprint 5 | 13 | Medium | High | Medium |
| WP-07 | ERS R2 (thin data model) / R4 (full) | Sprint 5 | 18 | Medium | Critical | High |
| WP-08 | ERS R2 (thin) / R4 (full) | Sprint 6 | 16 | Medium | Critical | Medium |
| WP-09 | ERS Release 4 | Sprint 7 | 14 | Medium | High | Medium |
| WP-10 | ERS R2 (thin) / R4 (full) | Sprint 8 | 20 | High | Critical | Critical |
| WP-11 | ERS R2 (thin) / R4 (full) | Sprint 9 | 16 | Medium | Critical | High |
| WP-12 | ERS Release 2 | Sprint 10 | 19 | High | Critical | High |
| WP-13 | ERS Release 3 | Sprint 11 | 15 | Medium | High | Medium |
| WP-14 | ERS Release 2 | Sprint 10 | 11 | Low | Medium | Medium |
| WP-15 | ERS R2 (scoped) / R3 (full) | Sprint 12 | 14 | High | High | High |
| WP-16 | ERS Release 4 | Sprint 13 | 13 | Medium | High | Medium |
| WP-17 | ERS R4 (full) / R5 (predictive) | Sprint 13 | 12 | Medium | Medium | Medium |
| WP-18 | ERS R1 (thin) / R4 (full) | Sprint 14 | 10 | Low | Medium | Medium |
| WP-19 | ERS Release 4 | Sprint 14 | 12 | Low | Medium | Low |
| WP-20 | ERS Release 4 | Sprint 15 | 11 | Low | Medium | Low |
| WP-21 | ERS Release 4 | Sprint 15 | 10 | Low | Medium | Low |
| WP-22 | ERS Release 5 | Sprint 16 | 14 | Medium | High | High |
| WP-23 | ERS R3 (thin) / R5 (full) | Sprint 17 | 22 | High | High | Critical |
| WP-24 | Continuous / closes at R5 | Sprint 18 | 12 | High | Critical | Critical |
| WP-25 | Continuous / closes at R5 | Sprint 19 | 8 | Low | High | Medium |

# 2.4  Table C — Governance & Deliverable

Every Work Package's dependencies, lifecycle status, ownership, and headline deliverable.

| WP | Dependencies | Status | Owner | Deliverable Summary |
| --- | --- | --- | --- | --- |
| WP-01 | None | Ready | Data Architect | Core schema, migrations, encryption at rest, backup/DR baseline (DDS Parts 1-9). |
| WP-02 | WP-01 | Ready | Solution Architect | API gateway, auth middleware, versioning and rate limiting (AIDS Parts 1-17). |
| WP-03 | None (parallel to WP-01/02) | Ready | DevSecOps Lead | CI/CD pipeline, environments, secrets vault, SAST/DAST gates (PDIB Part 14). |
| WP-04 | WP-01, WP-02, WP-03 | Ready | Technical Lead | Admin console, user/org management, configuration management. |
| WP-05 | WP-01-04 | Ready | Security Architect | RBAC engine, permission matrix, session management, access audit trail. |
| WP-06 | WP-01-05 (shell); WP-07 (full) | Defined | Backend Lead | Executive dashboard, KPI scorecards, decision briefs. |
| WP-07 | WP-01-05 | Defined | Technical Lead | Programme/zone/budget management, risk & issue registers, change requests. |
| WP-08 | WP-07 | Defined | Technical Lead | Project registration, Gantt timeline, milestone tracking. |
| WP-09 | WP-08 | Defined | Technical Lead | Task board, task detail view, my-tasks view. |
| WP-10 | WP-04, WP-09 | Defined | Technical Lead | Workflow designer, status tracker, routing engine. |
| WP-11 | WP-10, WP-04 | Defined | Technical Lead | Approval inbox, delegation, multi-stage approval chains. |
| WP-12 | WP-05, WP-11 | Defined | Backend Lead | Document library, upload and versioning, metadata, retention. |
| WP-13 | WP-12 | Defined | AI/KM Lead | Knowledge articles, lessons learned, templates, FAQs. |
| WP-14 | WP-03, WP-05 | Defined | Backend Lead | Media library, upload widget, gallery viewer. |
| WP-15 | WP-12, WP-13, WP-05 | Defined | AI/KM Lead | Global search, semantic index, filters. |
| WP-16 | WP-07, WP-08 | Defined | Backend Lead | Report catalogue, report builder, scheduled reports. |
| WP-17 | WP-16 | Defined | Backend Lead | Analytics dashboard, trend explorer, predictive models (R5). |
| WP-18 | WP-09, WP-10, WP-11 | Defined | Backend Lead | Notification center, preference management, delivery channels. |
| WP-19 | WP-04, WP-12 | Defined | Frontend Lead | Training catalogue, course player, certification tracking. |
| WP-20 | WP-18, WP-10 | Defined | Backend Lead | Ticket submission, ticket queue, my-tickets view. |
| WP-21 | WP-13, WP-20 | Defined | Frontend Lead | Help desk portal, FAQ browser, contextual help widget. |
| WP-22 | WP-07, WP-11, WP-12 | Defined | Security Architect | Public homepage, summary pages, document library, feedback form. |
| WP-23 | WP-13, WP-15, WP-05 | Defined | AI/KM Lead | RAG pipeline, knowledge graph, LLM integration, chat widget. |
| WP-24 | WP-01 through WP-23 (all) | Defined | QA Lead | Regression suite, performance test, penetration test, release readiness checklist. |
| WP-25 | WP-01 through WP-24 (all) | Defined | Programme Manager | Final documentation set, ADR log, 100% traceability matrix. |

# 2.5  How to Use This Catalogue

This catalogue is the entry point into the library. To find a Work Package's implementation detail — functional specification, API contracts, database schema, security controls, test plan, and Antigravity handoff — open its standalone document (Parts covering WP-01 through WP-25). Every such document follows the identical twenty-section template defined in Part 3.