VOLUME IV — ENTERPRISE ENGINEERING WORK PACKAGE LIBRARY (EWPL)

Part 5

Work Package Dependency Matrix

Enterprise System Management (ESM) Platform &

Central Knowledge Repository (CKR)

Special Agro-Industrial Processing Zones (SAPZ) Programme

Federal Republic of Nigeria

What Depends On What, What Delaying It Costs, and What Sits On the Critical Path

PART 5

Work Package Dependency Matrix

# 5.1  Purpose

| Purpose | Give a single, authoritative view of how the platform's twenty-five Work Packages depend on one another. |
| --- | --- |
| Business Value | Lets a Programme Manager answer, for any Work Package, 'what happens if this slips' without reconstructing the dependency graph from twenty-five individual documents. |
| Engineering Perspective | Consistent with, and does not restate, the technical dependency detail already fixed in MEKB Part 11; this matrix is the EWPL's own authoritative restatement at implementation-planning granularity. |
| Expected Outcome | Every Work Package's upstream dependency, downstream impact, delay risk, and critical-path status is answerable from one table. |

This matrix does not introduce a new dependency structure — it restates, once, in implementation-planning form, the dependency graph already fixed in MEKB Part 11 and consumed by the Enterprise Release Strategy's thin-slice analysis (ERS Part 1, Section 1.7) and the Enterprise Development Roadmap's build-order table. Where any other governing document's dependency statement and this matrix appear to disagree, the MEKB is authoritative and this matrix must be corrected.

# 5.2  The Full Dependency Matrix

| WP | Depends On | Enables | Risk if Delayed | Critical Path |
| --- | --- | --- | --- | --- |
| WP-01 | None | Every other Work Package (WP-02 through WP-25) — the platform's data backbone. | Blocks the entire programme; nothing else can begin. | Yes |
| WP-02 | WP-01 | Every module Work Package from WP-04 onward, which register endpoints behind this gateway. | Blocks all module development; no module can expose an API. | Yes |
| WP-03 | None (parallel to WP-01/02) | Every Work Package's ability to be tested and deployed. | Blocks testing and deployment platform-wide, though not module coding itself. | No — near-critical, must complete before Sprint 2 ends |
| WP-04 | WP-01, WP-02, WP-03 | WP-05, WP-10, WP-11, WP-19, and every module needing real users/organizations. | Blocks Security & Access Control and all downstream modules needing real user context. | Yes |
| WP-05 | WP-01 through WP-04 | Every module requiring access enforcement — effectively all of WP-06 through WP-25. | Leaves every subsequent module without enforced least-privilege access. | Yes |
| WP-06 | WP-01-05 (shell); WP-07 (full) | No downstream Work Package depends on WP-06. | Delays early executive visibility, but does not block other engineering work. | No — float available |
| WP-07 | WP-01 through WP-05 | WP-08, WP-16, WP-22, and the full build of WP-06. | Blocks Projects (WP-08) and the entire Programme Management delivery chain. | Yes |
| WP-08 | WP-07 | WP-09, WP-16, WP-22. | Blocks Tasks (WP-09) and project-level reporting. | Yes |
| WP-09 | WP-08 | WP-10 (full), WP-18. | Blocks the Workflow Engine's full build and Notifications' task-event source. | Yes |
| WP-10 | WP-04, WP-09 | WP-11, WP-12 (thin), WP-18, WP-20. | Blocks Approvals and every process requiring routed sign-off, including Documents. | Yes |
| WP-11 | WP-10, WP-04 | WP-12, and the full change-request process within WP-07. | Blocks Documents' review-before-publish requirement — the entire Release 2 headline capability. | Yes |
| WP-12 | WP-05, WP-11 | WP-13, WP-15, WP-19, WP-22. | Blocks Knowledge Repository, Search, Training content, and Public Portal. | Yes |
| WP-13 | WP-12 | WP-15, WP-21, and the knowledge foundation for WP-23. | Blocks Search's semantic layer and delays the AI Assistant's knowledge foundation. | Yes |
| WP-14 | WP-03, WP-05 | WP-22 (media assets). | Delays Public Portal's media capability only; does not block other modules. | No — float available |
| WP-15 | WP-12, WP-13, WP-05 | WP-23 (AI Assistant's retrieval foundation). | Blocks the AI Assistant's ability to retrieve from an indexed knowledge base. | Yes |
| WP-16 | WP-07, WP-08 | WP-17. | Delays Analytics; does not block the platform's core delivery chain. | No — float available |
| WP-17 | WP-16 | WP-06's full KPI maturity (optional integration). | Delays advanced analytics only. | No — float available |
| WP-18 | WP-09, WP-10, WP-11 | WP-20's escalation notifications. | Delays user awareness of platform events; does not block core delivery. | No — float available |
| WP-19 | WP-04, WP-12 | No downstream Work Package depends on WP-19. | Delays formal training rollout; peer-based onboarding continues in the interim. | No — float available |
| WP-20 | WP-18, WP-10 | WP-21 (ticket-volume data for FAQ prioritization). | Delays formal support-ticket tracking. | No — float available |
| WP-21 | WP-13, WP-20 | No downstream Work Package depends on WP-21. | Delays self-service deflection; Support (WP-20) absorbs the volume in the interim. | No — float available |
| WP-22 | WP-07, WP-11, WP-12 | No downstream Work Package depends on WP-22. | Delays external transparency and public-facing donor visibility. | No — float available, but must close before WP-24 |
| WP-23 | WP-13, WP-15, WP-05 | WP-24 (which requires WP-23 complete). | Blocks Release 5 and General Availability directly. | Yes |
| WP-24 | WP-01 through WP-23 (all) | WP-25. | Blocks final documentation closeout and General Availability. | Yes |
| WP-25 | WP-01 through WP-24 (all) | General Availability sign-off. | Blocks programme closeout and formal handover. | Yes |

# 5.3  Critical Path — Visual Summary

WP-01 -> WP-02 -> WP-04 -> WP-05 -> WP-07 -> WP-08 -> WP-09 -> WP-10 -> WP-11 -> WP-12 -> WP-13 -> WP-15 -> WP-23 -> WP-24 -> WP-25 15 of 25 Work Packages sit on the critical path — a delay to any one of these fifteen delays General Availability by the same amount, day for day. The remaining 10 Work Packages (WP-03, WP-06, WP-14, WP-16, WP-17, WP-18, WP-19, WP-20, WP-21, WP-22) carry schedule float but must still complete before WP-24, since WP-24's Definition of Ready requires WP-01 through WP-23 complete.

IMPORTANT Float is not the same as low priority. WP-05 (Security & Access Control) and WP-22 (Public Portal) illustrate the difference: WP-05 is Critical/Critical priority and on the critical path; WP-22 is High business priority but carries schedule float. A Work Package can be important to the business without being able to delay the programme's end date if it slips — and vice versa, a Work Package with modest visible business value (like WP-02, the API gateway) can be completely schedule-critical because of what it structurally unblocks.

# 5.4  Reading This Matrix Alongside the Release Strategy

The thin-slice pull-forwards documented in ERS Part 1, Section 1.7 — WP-10 and WP-11 into Release 2, WP-23 into Release 3 — do not appear as separate rows in this matrix because they are not separate Work Packages; they are partial-scope early deliveries of the same WP-10, WP-11, and WP-23 rows shown here. The dependency relationships in this matrix hold for both the thin-slice and full-scope delivery of each affected Work Package.