VOLUME IV — ENTERPRISE ENGINEERING WORK PACKAGE LIBRARY (EWPL)

Part 6

Work Package Execution Order

Enterprise System Management (ESM) Platform &

Central Knowledge Repository (CKR)

Special Agro-Industrial Processing Zones (SAPZ) Programme

Federal Republic of Nigeria

The Recommended Implementation Sequence, With Rationale, for All 25 Work Packages

PART 6

Work Package Execution Order

# 6.1  Purpose

| Purpose | Recommend the optimal implementation sequence for all twenty-five Work Packages, and justify each placement in plain terms. |
| --- | --- |
| Business Value | Gives Programme Management a single, defensible answer to 'why are we building this now and not sooner' for every Work Package in the library. |
| Engineering Perspective | Derived directly from Part 5's Dependency Matrix and consistent with the Sprint Roadmap already fixed in MEKB Part 9 and restated for release governance in ERS Part 6. |
| Expected Outcome | No Work Package's position in the schedule requires separate justification outside this table. |

# 6.2  The Full Execution Order

| WP | Sprint | Why This Order | Capability It Unlocks | Later Packages That Depend On It |
| --- | --- | --- | --- | --- |
| WP-01 | 1 | Nothing else can be written, tested, or exposed without a database to persist against. | Platform Data Backbone | All 24 remaining Work Packages |
| WP-02 | 2 | Every module needs one proven way to expose itself; establishing the contract pattern once, early, prevents twenty inconsistent implementations. | Platform Integration Backbone | WP-04 through WP-25 |
| WP-03 | 2 | Runs in parallel with WP-02 — nothing can be tested or deployed until build/release automation exists, but it does not itself depend on the data or API layer. | Build & Release Automation | Every Work Package's ability to ship |
| WP-04 | 3 | Every subsequent module needs real users and organizational context to be meaningfully built or tested against. | Platform Administration | WP-05, WP-10, WP-11, WP-19 |
| WP-05 | 4 | No module can enforce least-privilege access until roles and permissions exist and are enforced, not merely stored. | Access Governance | WP-06 through WP-25 (nearly all) |
| WP-06 | 5 | A read-only consumer of Programme data; its dashboard shell can be built in parallel against a mocked contract while WP-07 is still in progress. | Executive Visibility (shell) | None — terminal capability |
| WP-07 | 5 | The top-level organizing entity every project, zone, and budget line is scoped within. | Programme Delivery Chain | WP-08, WP-16, WP-22 |
| WP-08 | 6 | Cannot exist without a parent programme and zone. | Project Delivery | WP-09, WP-16, WP-22 |
| WP-09 | 7 | Cannot exist without a parent project. | Work Execution | WP-10, WP-18 |
| WP-10 | 8 | The shared orchestration layer every approval-style process will run on; must exist before Approvals can be built on top of it. | Process Orchestration | WP-11, WP-12 (thin), WP-18, WP-20 |
| WP-11 | 9 | The first and most demanding consumer of the Workflow Engine — proves the pattern before Documents depends on it. | Governance & Sign-off | WP-12, WP-07's change requests |
| WP-12 | 10 | The platform's document system of record; everything knowledge-related depends on it existing first. | Enterprise Content Management | WP-13, WP-15, WP-19, WP-22 |
| WP-13 | 11 | Organizes what Documents stores; cannot be built on an empty document store. | Organizational Knowledge | WP-15, WP-21, WP-23 |
| WP-14 | 10 | Independent of the document chain — runs in parallel with WP-12 since neither depends on the other. | Media Management | WP-22 |
| WP-15 | 12 | Indexes Documents and Knowledge Repository — cannot precede either. | Enterprise Discovery | WP-23 |
| WP-16 | 13 | Needs real Programme and Project data to report against. | Business Reporting | WP-17 |
| WP-17 | 13 | Builds on Reporting's data-access patterns rather than duplicating them. | Business Intelligence | None directly — optional WP-06 integration |
| WP-18 | 14 | Dispatches events already being produced by Tasks, Workflow, and Approvals — cannot precede any of its three event sources. | Platform Communication | WP-20 |
| WP-19 | 14 | Needs user records and a content store (Documents) to deliver courses through. | User Enablement | None — terminal capability |
| WP-20 | 15 | Needs Notifications and Workflow to escalate tickets. | User Support | WP-21 |
| WP-21 | 15 | Deflects tickets from Support — needs Support's ticket volume to know what to prioritize. | Self-Service Support | None — terminal capability |
| WP-22 | 16 | Publishes only Approvals-gated Programme and Document content — the last Work Package needing the full Release 2/4 content and governance chain. | External Transparency | None — terminal capability, but must close before WP-24 |
| WP-23 | 17 | Needs a stable, indexed knowledge base to retrieve from — built last among functional modules for this reason. | Intelligent Assistance | WP-24 |
| WP-24 | 18 | The full-platform inspection cannot happen until the whole building is standing — requires WP-01 through WP-23 complete. | Platform Quality Assurance | WP-25 |
| WP-25 | 19 | The handover binder closes out the paperwork the inspection (WP-24) confirmed is accurate. | Programme Documentation | General Availability sign-off |

# 6.3  Reading the Sequence

Three sprints in this sequence run two Work Packages in parallel: Sprint 2 (WP-02 and WP-03), Sprint 5 (WP-06 and WP-07), and Sprint 10 (WP-12 and WP-14). In every case, the parallel pair shares no dependency on each other — each depends only on Work Packages already closed in an earlier sprint. This is not a coincidence; it is the deliberate result of sequencing by dependency first, business value second, per the release philosophy fixed in ERS Part 1, Section 1.2.

Ten Work Packages in this sequence — WP-03, WP-06, WP-14, WP-16 through WP-22 — carry schedule float, meaning a delay to any one of them does not by itself delay General Availability, provided it still closes before WP-24 begins (Sprint 18). A Programme Manager under schedule pressure should look first at these ten Work Packages for any opportunity to add parallel capacity or defer non-essential scope, never at the fifteen critical-path Work Packages identified in Part 5.

RECOMMENDATION Treat this table, not intuition about business importance, as the basis for any resequencing conversation. WP-05 (Security & Access Control) is a clear example of a Work Package that must never be resequenced later despite having no single, dramatic business-facing feature of its own — nineteen of the remaining twenty Work Packages structurally depend on it.